**Release 2: Sprint 3 (29th September – 13th October)**

**Story ID 36: Updateable Profile [REOPENED]**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T55** | Provide functionality for students to update their parental guardian details in addition to their own details (if applicable). | 2 | 2 | 1st Oct 5:21pm | 2nd Oct 7:14pm |
| **T56** | Test and verify that tasks within the story have been completed. | 1 | 1 | 2nd Oct 7:14pm | 2nd Oct 7:59pm |
|  | Story Points: 2                                                                     Total Hours: | 3 | 3 |  |  |
|  |  | Completed by | | Daniel Wan | |

**Story ID 41: Full Access Account**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T57** | Change login page so that it checks the different user databases (staff, teachers, students) and assigns a different session variable based on the type of user logged in. | 2 | 2 | 7th Oct  8:26pm | 7th Oct  10:41pm |
| **T58** | Restrict webpages to the related user group using the new session variables (e.g. only staff can access management). Create a default administrator account that can create more. | 0.5 | 0.5 | 7th Oct  10:41pm | 7th Oct  11:00pm |
| **T59** | Add user lists, and other administrative features required by the client to the management page. | 1.5 | 2 | 8th Oct  10:07pm | 9th Oct  12:08am |
| **T60** | Test and verify that tasks within the story have been completed. | 1 | 0.5 | 9th Oct  12:08am | 9th Oct 12:47am |
|  | Story Points: 2                                                                    Total Hours: | 5 | 5 |  |  |
|  |  | Completed by | | Daniel Wan | | |

**Story ID 34: Create New Teacher Profile**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T61** | Set up the database to store both teacher and staff accounts and details. Create database documentation. | 1 | 1 | 12th Oct 7:54pm | 12th Oct 8:44pm |
| **T62** | Create page accessible by staff in the management tab that has them fill out a form a form with a new teacher’s details. Create a similar page that will create a staff profile. | 3 | 1.5 | 12th Oct 8:44pm | 12th Oct 10:03pm |
| **T63** | Test and verify that tasks within the story have been completed. | 1 | 0.5 | 12th Oct 10:03pm | 12th Oct 10:27pm |
|  | Story Points: 4                                                                      Total Hours: | 5 | 3 |  |  |
|  |  | Completed by | | Daniel Wan | |

**Story ID 12: Instrument hire catalogue [REOPENED]**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T64** | Add functionality that clicking an instrument allows students to enter their credit card information and hire the instrument, making it unavailable for hire. | 2 | 2 | 11th Oct 7:53pm | 11th Oct 9:05pm |
| **T65** | Test and verify that tasks within the story have been completed. | 1 | 1 | 11th Oct 9:05pm | 11th Oct 9:49pm |
|  | Story Points: 6                                                                     Total Hours: | 3 | 3 |  |  |
|  |  | Completed by | | Jason Chang | |

**Story ID 13: Ability to update instrument hire catalogue [REOPENED]**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T66** | Ensure that the instrument update and instrument delete functionality is fully implemented and meets user acceptance. | 2 | 2 | 9th Oct 9:32pm | 9th Oct 11:46pm |
| **T67** | Verify all tasks within the story have been completed | 1 | 1 | 9th Oct 11:46pm | 10th Oct 12:31am |
|  | Story Points: 4                                                                     Total Hours: | 3 | 3 |  |  |
|  |  | Completed by | | Jason Chang | |

**Release 2: Sprint 4 (13th October – 27th October)**

**Story ID 39:** **Make lesson bookings [REOPENED]**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T81** | Adjust Bookings database to add teacher ID and student ID with foreign key association on both. | 1 | 0.5 | 19th Oct 4:00pm | 19th Oct 4:35pm |
| **T82** | Added drop down menu displaying all teacher users currently in the database to select a relevant calendar. | 1 | 1.5 | 19th Oct  4:40pm | 19th Oct  6:15pm |
| **T83** | Adjusted calendar querying to display only bookings related to user select teacher ID. | 2 | 2.5 | 19th Oct  6:15pm | 19th Oct  8:45pm |
| **T84** | Added hidden capture on ‘Make Booking’ form to capture student ID into the database. | 0.5 | 0.5 | 19th Oct  9:00pm | 19th Oct  9:25pm |
| **T85** | Added key displaying what each colour means e.g. available, unavailable. | 1 | 0.5 | 19th Oct  9:25pm | 19th Oct  10:00pm |
| **T86** | Test and verify that tasks within the story have been completed. | 1 | 1 | 19th Oct  10:00pm | 19th Oct  11:00pm |
|  | Story Points: 5                                                                    Total Hours: | 6.5 | 6 |  |  |
|  |  | Completed by | | Alex Roubin | |

**Story ID 25: Feedback form**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T87** | Set up the database to store feedback (separate tables for feedback intended for staff or a teacher). Create database documentation. | 0.5 | 1 | 20th Oct 3:30pm | 20th Oct 4:31pm |
| **T88** | Create a page with a form for students to provide feedback. This form submits entered feedback to the database. | 2 | 2.5 | 20st Oct 4:31pm | 20st Oct 6:54pm |
| **T89** | Separate form into two for each recipient type (teachers and the school) based on story acceptance criteria. | 1.5 | 2 | 21st Oct 1:24pm | 21st Oct 3:37pm |
| **T90** | Test and verify that tasks within the story have been completed. | 1 | 1.5 | 21st Oct 3:37pm | 21st Oct 4:56pm |
|  | Story Points: 3                                                                   Total Hours: | 5 | 7 |  |  |
|  |  | Completed by | | Luke Yeh | |

**Story ID 19: Potential Teacher: Apply for Position at the school**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T91** | Set up the database to store job applications. Create database documentation. | 0.5 | 0.5 | 16th Oct 10:53pm | 16th Oct 11:27pm |
| **T92** | Create first stage of form where a job applicant may upload their resume which is stored on the webserver. | 2 | 2.5 | 16th Oct 11:27pm | 17th Oct 1:59am |
| **T93** | Create second stage of form where the job applicant fills in their details which is submitted to the database. | 1.5 | 1 | 18th Oct 7:54pm | 18th Oct 8:43pm |
| **T94** | Test and verify that tasks within the story have been completed. | 1 | 1 | 18th Oct 8:43pm | 18th Oct 9:48pm |
|  | Story Points: 4                                                                    Total Hours: | 5 | 5 |  |  |
|  |  | Completed by | | Jason Chang | |

**Story ID 26: Teacher: View Feedback**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T95** | Create a teacher profile page and link to a page where the teacher can view feedback. | 0.5 | 0.5 | 23rd Oct 4:34pm | 23rd Oct 4:57pm |
| **T96** | Match feedback provided by students for that specific teacher (using IDs) and show a table containing all the feedback. | 1 | 1 | 23rd Oct 4:57pm | 23rd Oct 5:48pm |
| **T97** | Test and verify that tasks within the story have been completed. | 0.5 | 0.5 | 23rd Oct 5:48pm | 23rd Oct 6:09pm |
|  | Story Points: 2                                                                    Total Hours: | 2 | 2 |  |  |
|  |  | Completed by | | Daniel Wan | |

**Story ID 35: Owner: View Feedback**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T98** | Create a management page where staff can view feedback. | 0.25 | 0.25 | 23rd Oct 7:49pm | 23rd Oct 8:05pm |
| **T99** | Show a table containing all the feedback provided by students. | 0.5 | 0.5 | 23rd Oct 8:05pm | 23rd Oct 8:27pm |
| **T100** | Test and verify that tasks within the story have been completed. | 0.25 | 0.25 | 23rd Oct 8:27pm | 23rd Oct 8:40pm |
|  | Story Points: 2                                                                    Total Hours: | 1 | 1 |  |  |
|  |  | Completed by | | Daniel Wan | |

**Story ID 13: Ability to update instrument hire catalogue [REOPENED]**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task ID** | **Task Description** | **Estimate** | **Taken** | **Start time** | **Finish time** |
| **T101** | Find the bug prevent instrument images from being uploaded, fix it and test it. | 1 | 2 | 25th Oct 7:44pm | 25th Oct 9:36pm |
| **T102** | Test and verify that tasks within the story have been completed. | 1 | 1 | 25th Oct  10:20pm | 25th  11:20pm |
|  | Story Points: 4                                                                   Total Hours: | 2 | 3 |  |  |
|  |  | Completed by | | Daniel Wan | |