## SprintInfo
Start Date | 2016-08-24 | Enter the start date for the sprint
End Date | 2016-09-08 | Enter the ending date for the sprint
Elapsed Days | 12
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 12
Number of Devs | 4
Utilization | 60% | Enter a value for the utilization of the team
Available Dev Hours | 230.4
Daily Dev Hours | 19.2

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
1 | 1 | 2 | Setup Linux based Server on Amazon EC2 cloud |  | 0 | Completed
1 | 2 | 3 | Install development tools onto platform i.e. LAMP stack, and share access to the server and software with all team members |  | 0 | Completed
1 | 3 | 1 | Setup GIT Hub Repository and invite all team members |  | 0 | Completed
1 | 4 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
1 | 5 | 1 | Install MySQL on web server |  | 0 | Completed
1 | 6 | 3 | Work out required databases, tables, table parameters etc. and set them up on the web server. |  | 0 | Completed
1 | 7 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
1 | 8 | 1 | Create homepage to index website off |  | 0 | Completed
1 | 9 | 2 | Create registration form to be displayed with appropriate fields |  | 0 | Completed
1 | 10 | 2 | Give ability for user to log in with previously created account |  | 0 | Completed
1 | 11 | 1 | Store registered information in MySQL Database associated to user |  | 0 | Completed
1 | 12 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
1 | 13 | 3 | Code button available for access for all users which queries database and returns list of all active teachers |  | 0 | Completed
1 | 14 | 2 | Write code for a search box that can filter teachers by instrument type, and potentially other categories that are deemed useful. |  | 0 | Completed
1 | 15 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
Total |  | 25 |  |  | 0

## BurnDownTable
Work Day | Estimate Burn Down | Actual Burn Down
2016-08-24 | 25 | 33
2016-08-25 | 23 | 32
2016-08-26 | 20 | 30
2016-08-27 | 20 | 30
2016-08-28 | 18 | 28
2016-08-29 | 18 | 28
2016-08-30 | 14 | 25
2016-08-31 | 13 | 23
2016-09-01 | 12 | 22
2016-09-02 | 12 | 22
2016-09-03 | 9 | 19
2016-09-04 | 7 | 13
2016-09-05 | 6 | 12
2016-09-06 | 4 | 9
2016-09-07 | 1 | 5
2016-09-08 | 0 | 0
Note on A2: PowerUps for Excel: Create one row per day in the sprint.