## SprintInfo
Start Date | 2016-09-09 | Enter the start date for the sprint
End Date | 2016-09-21 | Enter the ending date for the sprint
Elapsed Days | 9
Holidays | 0 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 9
Number of Devs | 4
Utilization | 60% | Enter a value for the utilization of the team
Available Dev Hours | 172.8
Daily Dev Hours | 19.2

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
2 | 25 | 2 | Code “profile update” GUI button onto personal profile web page. |  | 0 | Completed
2 | 26 | 3 | When updating their profile, display an editable form generated with their current details, and also allow them to change their password. |  | 0 | Completed
2 | 27 | 2 | Code GUI button update to replace existing personal information in the MySQL database. |  | 0 | Completed
2 | 28 | 1 | Verify all tasks within the story have been completed. |  | 0 | Completed
2 | 41 | 1 | Add ‘Bookings’ tab into header and align with other Buttons |  | 0 | Completed
2 | 42 | 3 | Code in functionality for Calendar to query bookings database |  | 0 | Completed
2 | 43 | 2 | Add available timeslots on each day |  | 0 | Completed
2 | 44 | 3 | Attach form to check bock when timeslot selected |  | 0 | Completed
2 | 45 | 2 | Code execution function to write booking array to database |  | 0 | Completed
2 | 46 | 1 | Code to record sessions student_id with booking |  | 0 | Completed
2 | 47 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
2 | 48 | 4 | Create an instrument catalogue page that is accessible from navigation bar which displays instruments that are available to hire (stored in the database). |  | 0 | Completed
2 | 49 | 3 | Create a search box that can filter instruments by instrument type, price, and other categories that are deemed useful. |  | 0 | Completed
2 | 50 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
2 | 51 | 1 | Have a page accessible by administrative accounts that allows them to submit a new instrument to the catalogue. |  | 0 | Completed
2 | 52 | 2 | In the instrument catalogue, create a button that opens a page that allows administrative accounts to update the instrument details. |  | 0 | Completed
2 | 53 | 2 | In the instrument catalogue, create a button that allows administrative accounts to delete instruments from the catalogue. |  | 0 | Completed
2 | 54 | 1 | Verify all tasks within the story have been completed |  | 0 | Completed
Total |  | 35 |  |  | 0

## BurnDownTable
Work Day | Estimate Burn Down | Actual Burn Down
2016-09-07 | 35 | 38
2016-09-08 | 34 | 37
2016-09-09 | 30 | 33
2016-09-10 | 28 | 30
2016-09-11 | 27 | 29
2016-09-12 | 27 | 29
2016-09-13 | 23 | 24
2016-09-14 | 21 | 22
2016-09-15 | 19 | 19
2016-09-16 | 15 | 15
2016-09-17 | 14 | 14
2016-09-18 | 6 | 9
2016-09-19 | 5 | 7
2016-09-20 | 2 | 4
2016-09-21 | 1 | 0
Note on A2: PowerUps for Excel: Create one row per day in the sprint.